MiniSim Phase 2

Revised Execution Plan

Fine-Tuning, Router Validation & Production Hardening

March 2026

Solo Operator • 12-Week Sprint

# Executive Summary

This document revises the original Phase 2 plan based on three critical findings from Phase 1:

- Single LLM beats swarm on easy questions. On the 10-question benchmark, a single Qwen 2.5 14B (Brier 0.0365) outperformed a 10-agent swarm (0.0412) on 7/10 questions. Swarm deliberation dilutes correct extreme estimates when agents already agree.

- Calibration exists but isn’t applied. The CalibrationTransformer was fitted on 544 questions (ECE 0.059 vs market 0.073) but is never used at inference time. Predictions go out uncalibrated.

- LLM mode is unevaluated at scale. The 544-question calibration run was offline-only. We have zero data on how LLM mode or the smart router performs on more than 10 questions.

The revised plan introduces a Phase 1.5 (Weeks 1–3) to close these gaps before beginning data collection and fine-tuning. The fine-tuning strategy targets both a single-shot forecaster and improved swarm agents, with the router selecting the right mode per question.

# Phase 1.5: Gap Closure (Weeks 1–3)

Before collecting training data or fine-tuning anything, we need to fix bugs, validate the router, and integrate calibration. This work is prerequisite — without it, Phase 2 data collection would be building on unverified assumptions.

## Week 1: Bug Fixes & Hardening

| Priority | Task | Hours |
| --- | --- | --- |
| P0 | Add missing json import in api.py (crashes /accuracy dashboard) | 0.5h |
| P0 | Revoke exposed Metaculus tokens, add .env to .gitignore | 0.5h |
| P0 | Fix KeyError: add geopolitics/crypto/other/climate/sports keys to BACKGROUNDS or add .get() with fallback in generate_population_offline | 2h |
| P1 | Replace 11 bare except blocks with logging.warning() calls | 3h |
| P1 | Remove demo-key-12345 default; require explicit MINISIM_API_KEYS env var | 1h |
| P1 | Delete survey_engine.py and run_survey.py (407+ dead lines) | 0.5h |
| P2 | Add integration tests: API endpoints, full pipeline offline, router | 6h |
| P2 | Integrate CalibrationTransformer into aggregator.py (apply Platt correction at inference) | 3h |

Week 1 total: ~16.5 hours

## Week 2: LLM Eval at Scale

Run the 544-question eval set through LLM mode. This is the most important missing data point — we cannot fine-tune what we cannot measure.

- Run calibration_at_scale.py --mode llm-ollama --agents 15 --rounds 2 on full 544-question dataset. Estimated runtime: ~4–6 hours on Apple Silicon with Qwen 2.5 14B.

- Run same dataset through the smart router (routed_predict) to measure routing distribution: what percentage of questions go to single_llm vs light_deliberation vs full_swarm?

- Compare LLM Brier, router Brier, and offline Brier on the same 544 questions. Gate check: LLM must beat offline by ≥15% to justify the cost.

- Validate router thresholds empirically. Sweep LOW_VARIANCE_THRESHOLD from 0.03–0.08 and HIGH_VARIANCE_THRESHOLD from 0.08–0.15. Find the threshold pair that minimizes aggregate Brier score.

Week 2 total: ~20 hours (mostly compute wait time)

Gate: If LLM mode doesn’t beat offline by 15% on 544 questions, re-evaluate fine-tuning strategy before proceeding.

## Week 3: PostgreSQL & Persistence

The API currently uses an in-memory dict for predictions and SQLite for logging. For production:

- Migrate database.py from SQLite to PostgreSQL (use asyncpg or psycopg2). Keep SQLite as fallback for local dev.

- Replace _predictions in-memory dict with Redis or PostgreSQL-backed prediction store.

- Add structured logging (JSON logs via structlog), health check improvements, and request tracing.

Week 3 total: ~18 hours

# Phase 2: Data Collection & Fine-Tuning (Weeks 4–12)

With bugs fixed, calibration integrated, router validated, and LLM mode measured at scale, we can begin the core Phase 2 work: collecting expert reasoning data and fine-tuning models.

## Fine-Tuning Strategy: Both + Router

Based on the Phase 1 finding that single LLM beats swarm on easy questions, we fine-tune two models and let the router select:

| Component | Purpose | Training Signal |
| --- | --- | --- |
| Single-Shot Forecaster | Fast, accurate point estimates for low-uncertainty questions (stdev < threshold). Replaces the generic ANCHOR_PROMPT. | (question, context, resolution) triples from Metaculus + Manifold + Kalshi. Trained to output calibrated P(YES). |
| Swarm Agent Model | Better initial forecasts per-persona for high-uncertainty questions. Each persona has distinct priors and reasoning style. | Expert reasoning transcripts: earnings calls, FOMC minutes, podcasts. Persona-anchored fine-tuning à la Stanford Generative Agents. |
| Router (not fine-tuned) | Variance-based routing. Thresholds validated from Phase 1.5 sweep. May add a small classifier later. | N/A — thresholds set from empirical sweep on 544 questions. |

## Week 4–5: Data Collection Infrastructure

Source 1: Metaculus Deep Scrape

Metaculus has ~30,000 resolved questions with community forecasts, resolution dates, and categories. This is the single best source for calibration training data.

- Scrape all resolved binary questions via Metaculus API (token auth already configured)

- Extract: question text, resolution, community median forecast, number of forecasters, resolution date, category

- Target: 5,000+ question-resolution pairs for single-shot forecaster training

Source 2: Expert Reasoning Transcripts

For the swarm agent model, we need persona-anchored reasoning — how an economist thinks differently from a geopolitical strategist on the same question. Sources:

- FOMC meeting minutes and transcripts (public, structured) — extract reasoning patterns for central bank watchers, macro economists

- SEC EDGAR earnings call transcripts — executive reasoning about market conditions, mapped to analyst/trader personas

- YouTube/podcast expert interviews (auto-transcribed via Whisper) — contrarian investors, VCs, policy experts

- Target: 500+ expert reasoning passages tagged by persona archetype, with quantitative probability mapping (Mauboussin scale)

Weeks 4–5 total: ~40 hours

## Week 6–7: Data Curation Pipeline

Raw transcripts are useless for fine-tuning. The curation pipeline converts unstructured expert reasoning into structured training examples.

- Build transcript parser: extract speaker segments, identify probabilistic language (“likely”, “unlikely”, “70% chance”), tag with persona archetype.

- Qualitative-to-quantitative mapping: convert verbal probabilities to numeric estimates using the Mauboussin probability scale (e.g., “likely” → 0.70–0.85).

- Quality filters: discard passages < 50 words, passages without clear directional reasoning, and duplicates.

- Format into fine-tuning-ready JSONL: {system: persona_prompt, user: question+context, assistant: {score, confidence, reasoning, key_factors}}.

Weeks 6–7 total: ~35 hours

## Week 8–9: Fine-Tuning Experiments

Single-Shot Forecaster

- Base model: Qwen 2.5 7B (or 14B if VRAM allows) via LoRA on Apple Silicon

- Training data: 5,000+ Metaculus resolved questions formatted as (question, context) → P(YES)

- Loss function: MSE on probability output (not cross-entropy on tokens)

- Eval: Brier score on held-out 500 questions. Must beat base Qwen single-shot (Brier ~0.037 from benchmark).

Swarm Agent Model

- Base model: Same Qwen 2.5, separate LoRA adapter

- Training data: 500+ persona-tagged reasoning passages + Metaculus resolution outcomes

- Key: persona conditioning via system prompt. The model learns to reason AS the persona, not just about the question.

- Eval: diversity score (stdev) must stay above 0.10 on mode collapse tests AND Brier must beat offline swarm (0.0997).

Weeks 8–9 total: ~40 hours

## Week 10–11: A/B Testing & Router Tuning

Run all three modes head-to-head on the full eval set:

| Mode | Questions | Expected Brier | Cost/Question |
| --- | --- | --- | --- |
| Offline (baseline) | All 544 | 0.0997 | $0 |
| Fine-tuned single-shot | Low-variance subset | < 0.035 | ~$0.001 |
| Fine-tuned swarm | High-variance subset | < 0.080 | ~$0.015 |
| Router (combined) | All 544 | < 0.065 | ~$0.005 avg |

Re-tune router thresholds on the fine-tuned models. The optimal split point will shift because fine-tuned single-shot should handle a wider range of questions than the generic anchor prompt.

Weeks 10–11 total: ~30 hours

## Week 12: Production Deploy & Documentation

- Deploy fine-tuned models via Ollama (local) or vLLM (cloud). Update LLMEngine to load LoRA adapters.

- Update /accuracy dashboard with fine-tuned model results. This is the sales asset.

- Write API documentation, deployment guide, and model card for the fine-tuned models.

- Run live backtest on 50 open Kalshi markets using the router + fine-tuned models. Track for 30 days.

Week 12 total: ~20 hours

# Time & Compute Budget

| Phase | Hours | Weeks |
| --- | --- | --- |
| Phase 1.5: Bug fixes & hardening | 16.5 | 1 |
| Phase 1.5: LLM eval at scale | 20 | 1 |
| Phase 1.5: PostgreSQL & persistence | 18 | 1 |
| Phase 2: Data collection infrastructure | 40 | 2 |
| Phase 2: Data curation pipeline | 35 | 2 |
| Phase 2: Fine-tuning experiments | 40 | 2 |
| Phase 2: A/B testing & router tuning | 30 | 2 |
| Phase 2: Production deploy | 20 | 1 |
| TOTAL | ~220 hours | 12 weeks |

## Compute Requirements

- LLM eval (Week 2): ~6 hours GPU time on Apple Silicon (M2/M3 Pro) running Qwen 2.5 14B via Ollama

- Fine-tuning (Weeks 8–9): LoRA on 7B model — feasible on 32GB M2 Pro. 14B may require cloud GPU (A100 spot instance, ~$1.50/hr, ~20 hours = $30)

- A/B testing (Weeks 10–11): ~12 hours inference time for 544 questions × 3 modes

# Risk Matrix

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| LLM mode doesn’t beat offline at scale | Medium | High | Gate check at Week 2. If fails, pivot to fine-tuning offline engine (alpha signals, archetype biases) instead of LLM. |
| Insufficient training data for persona fine-tuning | Medium | Medium | Fall back to single-shot forecaster only (still valuable). Accumulate persona data over time from API usage. |
| Fine-tuned model loses diversity (mode collapse) | High | High | Eval includes mode collapse tests. If diversity drops below 0.10 stdev, reduce fine-tuning epochs or use separate LoRA per persona tier. |
| Router thresholds don’t generalize | Low | Medium | Validate on 544 questions in Week 2. Can always fall back to full swarm for all questions (current default). |
| Metaculus API rate limits or access changes | Low | Low | Already have 544 questions cached. Manifold API is fully open. Can supplement with Polymarket resolved markets. |

# Success Criteria

Phase 2 is successful if all of the following are met:

| Metric | Target |
| --- | --- |
| Router+FT Brier (544 questions) | < 0.065 (vs 0.0997 offline baseline = 35% improvement) |
| Single-shot FT Brier | < 0.035 on low-variance questions (vs 0.0365 base Qwen) |
| Swarm FT Brier | < 0.080 on high-variance questions (vs 0.0997 offline) |
| Diversity preservation | Mode collapse test pass rate ≥ 7/8 (87.5%) |
| Calibration (ECE) | < 0.040 (vs 0.059 current swarm, 0.073 market) |
| API latency (p95) | < 30s for router mode (single-shot < 3s, full swarm < 60s) |
| Training data collected | ≥ 5,000 question-resolution pairs + 500 persona-tagged reasoning passages |

# Decision Points

The plan includes explicit go/no-go gates:

Week 2 gate: LLM eval results. If LLM Brier > offline Brier on 544 questions, do NOT proceed to fine-tuning LLM. Instead, pivot to fine-tuning the offline engine’s alpha signals and archetype biases.

Week 5 gate: Data sufficiency. If < 2,000 Metaculus questions or < 200 persona-tagged passages collected, extend data collection by 1–2 weeks before starting fine-tuning.

Week 9 gate: Fine-tuning quality. If fine-tuned single-shot doesn’t beat base Qwen on held-out set, increase training data or try different base model (Llama 3.1, Mistral) before A/B testing.

— End of document —